## Slide 1
TANGATA WHENUA ENGAGEMENT IN CONSULTATION
1996 – 2006
prepared & presented for pilot of Cultural Impact Assessment tool
4 December 2010 at Harataunga Marae

## Slide 4: Investment in Consultation Process
53 interactions/events
attendance at 17 public/iwi meetings
165 submissions + petition signed by 400 Māori landowners
establishment of Hau Kainga Working Group, Whaiti Kaimahi, Ngā Kaitiaki
signing of an MoU (… long-term relationship, utmost good faith, fair and equitable …)
internal consultation within iwi (Marae Trustees, NPkH, Hui Whakangungu x 4, Hui Motuhake x 3)
page-by-page analysis of Draft District Plan, Provisional District Plan, Transitional District Plan, Issues & Options Paper, Regulatory Committee papers/minutes, Variation #4 papers/Synopsis, Policy & Planning Committee Order Papers/minutes/ Summary of Decisions
15 letters, proposals, recommendations, 4 formal reports, 5 power point presentations
numerous discussions, teleconferences, visits with TCDC representatives (Mayors/Councillors/ staff/consultants), Environment Court, lawyers/QC, mediators, advisors, planners, politicians, MfE
participation in Variation #4, mediation hui, Environment Court “settlement” meeting
engagement in discussions about “Special Māori Purposes Zone”, “Harataunga Zone”, “Mana Whenua Zone”, “Iwi Kainga Zone”, “Iwi Management Plans”, RMA/LGA provisions for delegated authority
obtained & processed information under Official Information Act
made a DVD

## Slide 5: Sole objective of iwi engagement in TCDC consultation processes
to oppose the sub-division of Māori land in Harataunga

## Slide 6: Stages in the Consultation Process
Phase 1 (1996-1999): reassurance, optimisim, goodwill
Phase 2 (2000-2001): withdrawal, hesitancy, doubt, instability
Phase 3 (early 2003): salvage
Phase 4 (mid-2003): deception, exclusion, notification
Phase 5 (early 2006): new beginnings, hope, opportunity
Phase 6 (late 2006): disappointment, despair & disillusionment

## Slide 7: Harataunga 2A
PDP (1997) application to change zoning from Māori land to CVPA and establish 20-25 house sub-division
declined (2003) - land cannot take that type of development

## Slide 8: Harataunga 2C2B2C
Provisional District Plan (1997) application to change zoning from Māori land to CVPA and establish 20 house sub-division (at 4 x usual size) for relocation of baches when lease expired
    potential to establish 80 house sub-division
March 2003 Variation #4 Synopsis says the number of houselots will be reduced to 9
April 2003 Policy & Planning Committee pass resolution to exclude the public from meetings about settlement as “no third parties involved”
    Principal Planner advises against it
May 2003 second resolution to exclude the public, approved 18-house sub-division
    Planning staff note the density is “significantly beyond that contemplated in draft variation”, and recommends settlement is declined
15 September Environment Court is told “there was no opposition by any party” and grants consent order for structure plan
25 September 2003 TCDC hold public meeting to discuss Variation #4 - tangata whenua not informed above decision had already been made
28 October 2003 Tangata Whenua receive copy of EC Corrigendum to the Consent Order Paper for structure plan,
    invoked OIA, complaint to MfE, sought legal/QC advice, told objection too expensive, due process was followed
23 July 2005 TCDC approve resource consent for 18 house sub-division
    tangata whenua not notified despite letters requesting notification

## Slide 9: Harataunga 2C2B2D
July 2004 – John McLeod attends public meeting, wants to change zoning from Māori land to CVPA for 12 house sub-division
25 August 2004 – CVPA zone is approved in public document “Decisions on Variation #4”

## Slide 10: Harataunga 2B2
December 1999 – Robert McLeod attends hui-a-iwi, wants to rezone from Māori land to CVPA because it will “increase the value of his land”, no intention to sub-divide but will build 3 houses for his tamariki
July 2004 – TCDC hearing on planners recommendations contains reference to the application for CVPA zone
August 2004 – TCDC decline CVPA application
Oct 04 – Hobson Downs (Robert) lodges appeal against TCDC decision with Environment Court
Aug 05 – TCDC engage in mediation process
Dec 05 - structure plan for 15 house sub-division submitted
June 2006 - TCDC hold public meeting, invite submissions
    overwhelming opposition, 40 submissions plus petition (400)
July 2006 - EC decline request for tangata whenua to be party in proceedings because “the box wasn’t ticked”, recommend TCDC organise a mediation process
Nov 2006 – tangata whenua participate in mediation process, McLeods say (1) they will not sell the land for 13 years, (2) tangata whenua will have first right of refusal, (3) reserve contribution will be vested in the names of alienated share-holders
    tangata whenua told there will be no written record of meeting outcomes
2007 – TCDC/EC approve structure plan for 18 houses

## Slide 11
2 developers want subdivision
over 400 Māori landowners do not
subdivisions are approved!!